## Slide 1
Project Reporting
Fundamentals of
Business Process Outsourcing 102

## Slide 2: Session Objectives
At the end of this session, the student should be
able to:
Describe the parts of a project report
Explain “days to completion” as a method to assess percentage completed
Describe the contents of “project risk” section

## Slide 3: Parts of a Project Report
Status Report. “Where the project now stands”
  Schedule, budget status
  Percentage completed against plan
  Current open issues and challenges
Progress Report. “what the project team has accomplished”
  Tasks completed, tasks in flight
  Issues and challenges handled
Forecast. Prediction of “future status”
  Projected time and budget to completion
Risk Section. Specific risks and mitigations

## Slide 4: Class Activity
Create a project report for a hypothetical school concert one week before the event

## Slide 5: Challenges on Estimated % Completed
How to get a reasonably accurate estimate of percentage completed
Challenges:
  Most people over-estimate the work they have done. “50% completed” is difficult to verify
  Most will add buffers when asked for “time to completion;” conservative (lowest) estimate of percentage completed
  “Hours spent” versus total man-hours may not be an accurate basis for actual work done

## Slide 6: Conservative Measures
Goal of measure: good basis for assessing remaining work
Possible approaches:
“Task-binary” measure
  If work is completed, task is marked 100%. If task is not yet completed, it is marked 0%. Add the hours for unfinished tasks, calculate against total project hours
  Easy judgment whether task is done or not—versus subjective “% done”

## Slide 7: Conservative Measures
Possible approaches:
“Time to completion”
  Project manager is asked to estimate man-hours needed to completion
  Essentially a “re-forecast” of effort required given all factors—resource skill, availability of inputs, effectiveness of tools, quality of work
  Conservative because most PMs will add a buffer
  Stringent and good measure if the project manager is highly experienced and professional

## Slide 8: Risk to Projects
Risks are events that could have adverse effect “IF” they occur
  Risks that the project will not be completed, not completed on time, on budget, and with the right quality and scope
  If the risk events have already occurred (e.g., “not enough programmers”), that is a weakness which needs correction
Identified risks can be mitigated
  Mitigation actions minimize negative effect if risk event occurs
  Example: “cross-training” mitigates effect of loss of critical resources

## Slide 9: Sources of Risk
Internal: resources, equipment, facilities
  Unexpected attrition
  Unexpected equipment failure
  Loss of facilities

## Slide 10: Sources of Risk
External: suppliers, client stakeholders, market, political events, acts of God
  Supplier failure to deliver right inputs/resources on time at right price and with right quality
  Unexpected change in client senior management, unexpected loss of support, change in executive direction for the project
  Severe market downturn leading to change in project value
  Unexpected political disruptions, strikes, coup, rebellion, severe crime wave
  Storms, typhoons, fire leading to project disruption

## Slide 11: Risk Section
Lists specific internal and external risks to the project
  Stakeholders (sponsor, business leaders) assess if the significant risks have been considered by the project team
For each risk, state the mitigation action
  Stakeholders assess if the mitigations are correct/sufficient
  Stakeholders assess if the amount spent for mitigations is commensurate to the cost of the risk

## Slide 12: Summary
Parts of a project report
  Status report, progress report, forecast, risk section
“Days to completion”
  Goal is a conservative measure for effort required to complete the project
  Task-binary measure (count hours for unfinished tasks)
  Man-hours to complete (refreshed estimate of time to complete)
“Project risk” section
  Specific internal and external risks to the project
  Mitigation for each risk

## Slide 13: References
  A Guide to the Project Management Body of Knowledge (referred to as “PMBOK”), Project Management Institute, 2000 Edition.