## Slide 1
Planning Processes
Fundamentals of
Business Process Outsourcing 102

## Slide 2: Session Objectives
At the end of this session, the student should be
able to:
Enumerate the critical elements in a project plan
Define core planning processes
Define facilitating planning processes

## Slide 3: What is a Project Plan
Project plan is an “approved document to manage project execution” [PMBOK]
Can and will change over time as the environment, output scope, inputs, resources change
A good project plan will help the project manager and the project organization respond to changes with least delivery (time, cost) risk

## Slide 4: Critical Planning Elements
Time
  Time is always short. “Time needed” tends to expand towards “time available.” Hence need to keep buffers low
  Project timeline. Initially agreed final delivery date is expanded to show the delivery dates of the phases and sub phases
  Critical path. Flow and timing/completion of prerequisite activities will determine the critical path in terms of time
  Buffers. Project leaders provide buffers between activities to cover unexpected external events (resources getting sick, “acts of God” (typhoons, floods)

## Slide 5: Critical Planning Elements
Resources
  Resource is always scarce; most scarce resource is generally people
  Project plans help visualize realistic assignment of scarce resources across multiple activities (and projects)
  Resource plans surface potential contention for resources up front than to face the later problem of unrealistic deadlines due to lack of resources

## Slide 6: Critical Planning Elements
Cost
  Money is always not enough (generally). But between time and resource (people), money is often easier to get
  One can get more money but a project cannot normally be hurried by mere throwing bodies into it
  In global projects, resource costs account for the bulk of project budgets

## Slide 7: Core Planning Processes
Planning processes that must be done for all projects
Answer the questions:
  What output must be delivered: scope plan (scope definition, work breakdown)
  What activities to produce it and how long: activity plan (activity definition, activity sequencing, activity and total duration)
  Who will do the activities: resource plan (resource requirements, resource-activity scheduling)
  How much will it cost: cost plan (cost estimation)

## Slide 8: Facilitating Planning Processes
Planning processes that are not performed all the time but well-managed projects have them
Answer the questions:
  Who manages the project, who reports to whom: organization plan (reporting lines, project roles and responsibilities)
  What resources (staff) need to be hired or contracted and by when: staffing plan (also called “recruitment plan”)
  Which quality standards to follow: quality plan (standards, measures, transparency)
  How will risk be identified, managed: risk management plan

## Slide 9: Facilitating Planning Processes
Answer the questions: (Continued)
  What will be communicated, to whom, when, how, by whom: communications plan
  What services, goods, materials need to be bought and when: procurement plan (what to buy, when, from which potential sources, estimate of how much

## Slide 10: Group Activity
By teams, create the project plan for the case below:
A school concert for the whole evening: 4 name bands and 4 student bands, opening remarks from the school president, closing remarks from the student council president. Each of the bands require a visit and conversation to explain the purpose of the concert and what value the exposure will have for them. One of the bands is in a different city. The 4 student bands are still to be selected; a contest for the audition will have to be organized. You have to generate funds from sponsorships and booth fees to pay for the cost of the concert. This concert will occur 70 days from now.
This project will require sub project plans. The intent is that each team member has to do 1 or more project plans and they have to be consistent.

## Slide 11: To Do:
Create the project objectives. Formulate the success criteria.
Create a 10-week project plan. Be realistic about the time allocation.
Initial Gantt Chart..

## Slide 12: Summary
Critical elements in a project plan
  Time, resources, and cost
Core planning processes
  Planning processes that must be done for all projects
  Scope plan, activity plan, resource plan, cost plan
Facilitating planning processes
  Not performed always but well-managed projects have them
  Organization plan, staffing plan, risk management plan, quality plan, communication plan and procurement plan

## Slide 13: References
  A Guide to the Project Management Body of Knowledge (referred to as “PMBOK”), Project Management Institute, 2000 Edition. All of the principles/key terms/concepts presented in this set of sessions on project management come from PMBOK unless explicitly attributed to other references.